## SOW Template Example
Population Domain: |  | Women/Maternal Health
Title V Priority Area | Increase the number of women who receive recommended clinical care components at the postpartum visit and appropriate referrals
Objective | By 2030, 90% of women who attended a postpartum visit will have done so within 12 weeks of birth and 70% of women who attended a postpartum checkup will also have received the recommended clinical care components.
NPM/SPM | Postpartum Visit (PPV) – A) Percent of women who attended a postpartum checkup within 12 weeks after giving birth and B) Percent of women who attended a postpartum checkup and received recommended clinical care components.
Baseline Narrative | Nevada's postpartum preventive visit rate remains below the national average. Women experience barriers including limited access to providers, lack of awareness of postpartum preventive care recommendations, and challenges navigating available services.
SMART Goal | Contribute to increasing the percentage of women receiving a preventive medical visit within 12 months after pregnancy through implementation of evidence-based postpartum education and referral practices among participating hospitals by September 30, 2027.
Evidence-Based Strategy | Implement standardized postpartum education and referral practices through participating hospitals and clinical partners to increase awareness and utilization of preventive postpartum care.
Evidence Supporting Strategy | The American College of Obstetricians and Gynecologists (ACOG) recommends comprehensive postpartum care that includes standardized patient education and care coordination. Evidence published through the HRSA Title V Evidence Center demonstrates that standardized discharge education and referral practices improve postpartum follow-up and continuity of care.
Evidence-Based/Informed Strategy Measure (ESM) | Increase the percentage of participating hospitals that have fully implemented standardized postpartum education and referral protocols, as demonstrated through fidelity monitoring, from 40% at baseline to 80% by September 30, 2027.
ESM Rationale | Increasing the percentage of hospitals implementing standardized postpartum education and referral protocols is expected to improve patient awareness of recommended postpartum preventive care, increase referral completion, and contribute to higher rates of preventive visits within 12 months after pregnancy.
ESM Indicator | Percentage of participating hospitals implementing standardized postpartum education and referral protocols
Baseline | 40%
Annual Target | 80%
Data Source | Hospital implementation reports; program monitoring records
Reporting Frequency | Quarterly
Evaluation Methodology | Monitor implementation through quarterly implementation reports, fidelity assessments, site monitoring, and documentation reviews to evaluate progress toward the annual ESM target and identify opportunities for continuous quality improvement.
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes
1.1 Develop standardized postpartum education materials | Public Health Services/Systems | Participating hospitals adopt and implement the standardized postpartum education toolkit. | ≥90% of participating hospitals adopt and begin using the toolkit by the end of Quarter 2. | Hospital implementation survey; site monitoring reports | Education toolkit | Quarter 1 | Number and percentage of hospitals adopting the toolkit | Increased provider awareness of standardized postpartum education
1.2 Train hospital discharge staff | Public Health Services/Systems | Identified discharge staff complete training and demonstrate competency in standardized postpartum education and referral practices. | ≥90% of identified staff complete training and ≥85% achieve competency on post-training assessment. | Training attendance records; pre-/post-assessments; competency validation | Four training sessions completed | Quarters 1–2 | Number and percentage of discharge staff trained | Increased provider knowledge and confidence implementing standardized postpartum education and referral practices
1.3 Implement standardized referral protocol | Enabling Services | Participating hospitals consistently implement the standardized postpartum referral protocol. | ≥80% of participating hospitals implement the protocol (ESM) and ≥90% of eligible postpartum patients receive documented education and referral prior to discharge. | Hospital implementation reports; chart audits; referral documentation | Referral protocol adopted | Quarter 2 | Number and percentage of hospitals implementing the protocol; Approximate number of staff utilizing protocol | Increased implementation of standardized postpartum referral practices
1.4 Conduct quarterly technical assistance | Public Health Services/Systems | Participating hospitals address implementation barriers identified through monitoring and technical assistance. | ≥90% of identified corrective actions are completed within one reporting quarter. | Technical assistance logs; corrective action plans; follow-up monitoring reports | TA summaries and action plans | Quarterly | Number of TA sessions completed; number of corrective actions completed | Improved implementation fidelity and continuous quality improvement

## Women-Maternal Health #1
Population Domain: |  | Women/Maternal Health
Title V Priority Area | Increase the number of women who receive recommended clinical care components at the postpartum visit and appropriate referrals
Objective | By 2030, 90% of women who attended a postpartum visit will have done so within 12 weeks of birth and 70% of women who attended a postpartum checkup will also have received the recommended clinical care components.
NPM/SPM | Postpartum Visit (PPV) – A) Percent of women who attended a postpartum checkup within 12 weeks after giving birth and B) Percent of women who attended a postpartum checkup and received recommended clinical care components.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Women-Maternal Health #2
Population Domain: |  | Women/Maternal Health
Title V Priority Area | Improve access to prenatal and maternal health services
Objective | By 2030, 80% of pregnant women in Nevada will receive their prenatal care beginning in the first trimester.
NPM/SPM | Prenatal Care (PNC) – Percent of mothers who reported late or no prenatal care.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Perinatal-Infant Health #1
Population Domain: |  | Perinatal/Infant Health
Title V Priority Area | Increase breastfeeding rates among mothers.
Objective | By 2030, 83% of infants will ever be breastfed and 25% of infants will be breastfed exclusively for 6 months.
NPM/SPM | Breastfeeding (BF) – A) Percent of infants who are ever breastfed and B) Percent of children, ages 6 months through 2 years, who were breastfed exclusively for 6 months
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Perinatal-Infant Health #2
Population Domain: |  | Perinatal/Infant Health
Title V Priority Area | Reduce substance use during and after pregnancy
Objective | By 2030, reduce the percent of women who report using tobacco, alcohol, or illicit substances during pregnancy to 3.6%.
NPM/SPM | Substance Use Disorder (SUD) – Percent of women who use substances during pregnancy.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Perinatal-Infant Health #3
Population Domain: |  | Perinatal/Infant Health
Title V Priority Area | Increase safe sleep practices.
Objective | By 2030, increase safe sleep practices as follows: Back sleep position to 68.3%; Approve sleep surface to 29.5%; No soft object/loose bedding to 69.2%; and Room-sharing to 83.2%.
NPM/SPM | Safe Sleep (SS) – A) Percent of infants placed to sleep on their backs, B) Percent of infants placed to sleep on a separate approved sleep surface, C) Percent of infants placed to sleep without soft objects or loose bedding, and D) Percent of infants room-sharing with an adult.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Child Health #1
Population Domain: |  | Child Health
Title V Priority Area | Increase access to affordable and nutritious foods among school-aged children.
Objective | By 2030, 67% of children in Nevada will live in households where food was sufficient in the past year.
NPM/SPM | Food Sufficiency (FS) – Percent of children, ages 0 through 11, whose households were sufficient in the past year.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Child Health #2
Population Domain: |  | Child Health
Title V Priority Area | Increase physical activity among school-aged children.
Objective | By 2030, 20% of children, ages 6 through 11, will be physically active for at least 60 minutes per day in Nevada.
NPM/SPM | Physical Activity (PA) – Percent of children, ages 6 through 11, who are physically active at least 60 minutes per day.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Child Health #3
Population Domain: |  | Child Health
Title V Priority Area | Promote a Medical Home
Objective | By 2030, 20% 35% of children with and without special health care needs, ages 0 through 17, will have a medical home.
NPM/SPM | Medical Home (MH) – Percent of children with and without special health care needs, ages 0 through 17, who have a medical home.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Adolescent Health #1
Population Domain: |  | Adolescent Health
Title V Priority Area | Increase referrals and appropriate care for adolescents.
Objective | By 2030, 67% of adolescents, ages 12 through 17, will have had a preventive visit in the past year.
NPM/SPM | Adolescent Well-Visit (AWV) – Percent of adolescents, ages 12 through 17, with a preventive medical visit in the past year.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Adolescent Health #2
Population Domain: |  | Adolescent Health
Title V Priority Area | Improve access to resources and services around sexual health and reproductive health.
Objective | By 2030, the rate of sexually transmitted infections (STIs) among adolescents ages 12-17 will be 500 per 100,000 population.
NPM/SPM | Sexually Transmitted Infections (STI) – Rate of STIs for adolescents ages 12-17 years
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## CSHCN #1
Population Domain: |  | Children with Special Health Care Needs
Title V Priority Area | Promote a Medical Home
Objective | By 2030, 35% of children with special health care needs, ages 0 through 17, will have a medical home.
NPM/SPM | Medical Home (MH) – Percent of children with special health care needs, ages 0 through 17, who have a medical home.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Cross-Cutting
Population Domain: |  | Cross-Cutting/Systems Building
Title V Priority Area | Improve workforce development; Improve data collection and management; Strengthen partnerships; etc.
Baseline Narrative
SMART Goal
Evidence-Based Strategy
Evidence Supporting Strategy
Evidence-Based/Informed Strategy Measure (ESM)
ESM Rationale
ESM Indicator
Baseline
Annual Target
Data Source
Reporting Frequency
Evaluation Methodology
Activity | Service Type (Public Health / Enabling Services) | Performance Indicator | Performance Target | Data Source | Deliverable | Timeline | Outputs | Expected Outcomes

## Dropdown (hidden)
Domain | Services
Women/Maternal Health | Public Health Services/Systems
Perinatal/Infant Health | Enabling Services
Child Health | Not Applicable
Adolescent Health
Children with Special Health Care Needs
Cross-Cutting/Systems Building